## Original
Week |  | Release #
2020-06-29 | Deploy first thing | 1
2020-06-30 | Deploy first thing
2020-06-30 | Prepare the files | 2
2020-06-30 | Run the test files | 3
2020-07-01 | Put the ML flask app | 4
2020-07-03 | Deploy the ML flask in azure | 5
2020-07-04 | Deploy the ML flask in azure | 6
2020-07-06 | Deploy the ML flask in azure | 7
2020-07-09 | Deploy the ML flask locally | 8
2020-07-10 | Deploy the ML flask locally | 9
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Create the pipeline | 1 | 1 | Deploy first thing | Demo every monday
Put the task in trello | 2 | 2 | Deploy first thing | Weekly planning after demo
Run pipeline without error | 3 | 1 | Deploy first thing | Consumer/Stakeholder Release every 2 weeks
Check the rest of the project | 4 | 1 | Deploy first thing | Tickets represents no more than 3 days work
Add Makefile | 1 | 1 | Prepare the files
Add requirements.txt | 2 | 1 | Prepare the files
Add hello.py | 3 | 1 | Prepare the files
Add test_hello.py | 4 | 1 | Prepare the files
Fix the sintax of Makefile and test_hello.py | 1 | 2 | Run the test files
Enable GitHub Action | 2 | 2 | Run the test files
Modifying README.md to test GitHub Actions UI | 3 | 2 | Run the test files
Adding Status badge | 4 | 2 | Run the test files
Replacing scaffolding code with Flask Machine Learning code | 1 | 2 | Put the ML flask app
Update github action pythonapp.yml | 2 | 1 | Put the ML flask app
Creation of the python webapp | 1 | 2 | Deploy the ML flask in azure
Set up CI with Azure Pipelines | 2 | 3 | Deploy the ML flask in azure
Update values of port in app.py | 3 | 1 | Deploy the ML flask in azure
Create the azure pipeline | 4 | 1 | Deploy the ML flask in azure
Deploy the app locally | 1 | 2 | Deploy the ML flask locally
Deploy the app using docker | 2 | 2 | Deploy the ML flask locally
Complete the README.md | 3 | 3 | Deploy the ML flask locally
Update the project plan | 4 | 1 | Deploy the ML flask locally

## Final
Week |  | Release #
2020-06-29 | Deploy first thing | 1
2020-06-30 | Deploy first thing
2020-06-30 | Prepare the files | 2
2020-06-30 | Run the test files | 3
2020-07-01 | Put the ML flask app | 4
2020-07-03 | Deploy the ML flask in azure | 5
2020-07-09 | Deploy the ML flask in azure | 6
2020-07-11 | Deploy the ML flask in azure | 7
2020-07-13 | Deploy the ML flask locally | 8
2020-07-16 | Deploy the ML flask locally | 9
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Create the pipeline | 1 | 1 | Deploy first thing | Demo every monday
Put the task in trello | 2 | 2 | Deploy first thing | Weekly planning after demo
Run pipeline without error | 3 | 1 | Deploy first thing | Consumer/Stakeholder Release every 2 weeks
Check the rest of the project | 4 | 1 | Deploy first thing | Tickets represents no more than 3 days work
Add Makefile | 1 | 1 | Prepare the files
Add requirements.txt | 2 | 1 | Prepare the files
Add hello.py | 3 | 1 | Prepare the files
Add test_hello.py | 4 | 1 | Prepare the files
Fix the sintax of Makefile and test_hello.py | 1 | 2 | Run the test files
Enable GitHub Action | 2 | 2 | Run the test files
Modifying README.md to test GitHub Actions UI | 3 | 2 | Run the test files
Adding Status badge | 4 | 2 | Run the test files
Replacing scaffolding code with Flask Machine Learning code | 1 | 2 | Put the ML flask app
Update github action pythonapp.yml | 2 | 1 | Put the ML flask app
Creation of the python webapp | 1 | 3 | Deploy the ML flask in azure
Set up CI with Azure Pipelines | 2 | 3 | Deploy the ML flask in azure
Update values of port in app.py | 3 | 3 | Deploy the ML flask in azure
Create the azure pipeline | 4 | 3 | Deploy the ML flask in azure
Deploy the app locally | 1 | 2 | Deploy the ML flask locally
Deploy the app using docker | 2 | 2 | Deploy the ML flask locally
Complete the README.md | 3 | 3 | Deploy the ML flask locally
Update the project plan | 4 | 1 | Deploy the ML flask locally